PROCUREMENT TIMETABLE – IT Hardware, Software and Consumables

Start Date: May 2024

Completion Date: October 2024

Total Time: 6 months

Current Contract Expiry Date – 31st October 2024

| Description of Event | Date | Duration |
| --- | --- | --- |
| Issue contract notice via FTS | 10/05/2024 – 09/06/2024 | 30 days |
| Issue PQQ Ariba | 10/06/2024 | Min 15 calendar days |
| Deadline for submission of PQQ | 26/06/2024 |  |
| Download PQQ submissions | 27/06/2024 | 0.5 days |
| Evaluation of PQQ submissions | 28/06/2024 – 12/07/2024 | 2+ weeks |
| S02 Approval | 15/07/2024 – 17/07/2024 | 3 days |
| Notification to successful/unsuccessful bidders | 18/07/2024 – 19/07/2024 | 1 – 2 days |
| Issue invitation to tender via Ariba | 22/07/2024 | 3 weeks, 10 days minimum |
| Deadline for supplier clarification questions | 29/07/2024 |  |
| Deadline to circulate all suppliers Clarification questions | 31/07/2024 |  |
| Tender return date | 09/08/2024 |  |
| Download Returns from Ariba & circulate to stakeholders | 09/08/2024 | 1 day |
| Evaluations & Contract Clarifications | 12/08/2024 – 23/08/2024 | 2 weeks |
| SO3 Approval | 26/08/2024 – 28/08/2024 | 3 days |
| Issue Standstill Letters | 29/08/2024 – 09/09/2024 | 10 calendar days |
| Send formal award letter to the successful bidder/s | 10/09/2024 | 1 day |
| Contract Issue and Negotiations | September 2024 | 1 – 4 weeks |
| SO4 Approval | September 2024 |  |
| Send fully signed contract to bidder | October 2024 | 1 day |
| Publish Contract Award Notice via OJEU | October 2024 | 1 day |
| Contract Start Date | 1st November 2024 |  |

*Subject to Change *

Notes: